## Project Checklist
Project Delivery Checklist
Fill in Status, Owner, Target Date and Remarks.
S.No | Phase | Task | Responsible | Status | Owner | Target Date | Remarks
1. Project Initiation
1 | 1. Project Initiation | Receive resource count / capacity allocation from Management | Engineering Manager | Completed | Arjun Mehta | 2026-09-05 | Four engineers allocated for the first release
2 | 1. Project Initiation | Decide and finalise the project team (Dev, QA, Architect, Lead) | Engineering Manager | Not Started
3 | 1. Project Initiation | Confirm PRD, User Stories, Personas, Business Objectives are ready | Product Team | Completed |  |  | evidence: docs/product/PRD.md
4 | 1. Project Initiation | Confirm Functional & Non-Functional Requirements are documented | Product Team | Completed |  |  | evidence: docs/product/PRD.md
5 | 1. Project Initiation | Confirm Data Models / Data Points and Acceptance Criteria are defined | Product Team | Not Started
6 | 1. Project Initiation | Confirm UI/UX references are shared (if applicable) | Product Team | Not Started
7 | 1. Project Initiation | Schedule and set up the Project Kickoff / Handover meeting | Team Lead | Not Started
8 | 1. Project Initiation | Conduct handover walkthrough: business requirements, user journeys, functional scope | Product Team | Not Started
9 | 1. Project Initiation | Walk through technical constraints, timelines, milestones, deliverables, dependencies | Product Team | Not Started
10 | 1. Project Initiation | Raise all open questions from Dev and QA during handover | Team Lead | Not Started
11 | 1. Project Initiation | Ensure all requirements are thoroughly clarified with the team; close every clarification | Team Lead | Not Started
12 | 1. Project Initiation | Obtain formal approval / sign-off on PRD and User Stories | Product Team | Not Started
13 | 1. Project Initiation | Confirm development can begin (handover done, questions closed, PRD approved) | Team Lead | Not Started
2. Project Setup
14 | 2. Project Setup | Create the shared project Drive folder with the standard structure | Team Lead | Not Started
15 | 2. Project Setup | Create sub-folders: Product, Technical, Architecture, API Documentation, UI/UX, QA | Team Lead | Not Started
16 | 2. Project Setup | Create sub-folders: Analytics, Security, Deployment, Release Notes, Client Deliverables, Meeting Notes | Team Lead | Not Started
17 | 2. Project Setup | Apply document naming convention and version history to all documents | Team Lead | Completed |  |  | evidence: docs/deliverables/versions.json
18 | 2. Project Setup | Create the dedicated git group for the client (PascalCase) | Team Lead | Not Started
19 | 2. Project Setup | Create Client subgroup repositories (Web / Android / iOS) | Team Lead | Not Started
20 | 2. Project Setup | Create Server subgroup repositories (API, Auth, Notification, Scheduler, Worker) | Team Lead | Not Started
21 | 2. Project Setup | Verify all group / subgroup / repo names follow PascalCase and are descriptive | Team Lead | Not Started
22 | 2. Project Setup | Create dedicated cloud projects: Dev, QA, Prod (PascalCase naming) | Team Lead | Not Started
23 | 2. Project Setup | Confirm cloud project naming with Engineering Manager if any uncertainty | Team Lead | Not Started
24 | 2. Project Setup | Provision all cloud resources within the correct cloud project | Developer | Not Started
25 | 2. Project Setup | Create the project entry in the tracker | Team Lead | Not Started
26 | 2. Project Setup | Set up the tracker hierarchy: Project > PRD > User Stories > Tasks / Bugs > Releases | Team Lead | Not Started
3. Planning & Estimation
27 | 3. Planning & Estimation | Create User Stories with clear, testable Acceptance Criteria | Product Team | Completed |  |  | evidence: docs/product/backlog.md
28 | 3. Planning & Estimation | Add all User Stories to the tracker and link them to the PRD | Team Lead | Not Started
29 | 3. Planning & Estimation | Break each User Story into Development Tasks, QA Tasks and Bugs | Team Lead | Not Started
30 | 3. Planning & Estimation | Create all tasks within one working day of handover completion | Team Lead | Not Started
31 | 3. Planning & Estimation | Add Description, Acceptance Criteria, Priority, Estimated Effort, Dependencies to each task | Team Lead | Not Started
32 | 3. Planning & Estimation | Verify every task is linked to a User Story | Team Lead | Not Started
33 | 3. Planning & Estimation | Conduct the Sprint Planning meeting and distribute tasks | Team Lead | Not Started
34 | 3. Planning & Estimation | Assign work considering skillset, workload, sprint capacity and timelines | Team Lead | Not Started
35 | 3. Planning & Estimation | Confirm each Developer and QA Engineer understands their assigned scope | Developer | Not Started
4. Solution Design
36 | 4. Solution Design | Prepare UI/UX designs using Claude Design | Developer | Not Started
37 | 4. Solution Design | Review and obtain Product team approval on UI/UX designs | Product Team | Not Started
38 | 4. Solution Design | Route any post-approval design change through the change management process | Team Lead | Not Started
39 | 4. Solution Design | Prepare the High-Level Design (HLD) | Team Lead | Blocked | Kavya Rao | 2026-09-30 | Waiting on Northwind to confirm the billing export feed; the HLD assumption is not signed off by the client
40 | 4. Solution Design | HLD: System Architecture and Service Boundaries | Team Lead | Completed |  |  | evidence: docs/design/orders-hld.md
41 | 4. Solution Design | HLD: Database Design | Team Lead | Not Started
42 | 4. Solution Design | HLD: External Integrations | Team Lead | Not Started
43 | 4. Solution Design | HLD: Security Considerations | Team Lead | Not Started
44 | 4. Solution Design | HLD: Deployment Architecture | Team Lead | Not Started
45 | 4. Solution Design | HLD: Scalability Strategy | Team Lead | Not Started
46 | 4. Solution Design | HLD: Observability Architecture | Team Lead | Not Started
47 | 4. Solution Design | HLD: Analytics Architecture | Team Lead | Not Started
48 | 4. Solution Design | Prepare Low-Level Design (where applicable) | Developer | Not Started
49 | 4. Solution Design | Prepare Architecture Diagram | Team Lead | Not Started
50 | 4. Solution Design | Confirm the standard technology stack; get Architect + EM review for any deviation | Team Lead | Not Started
51 | 4. Solution Design | Obtain architecture approval before development begins | Team Lead | Not Started
5. Infrastructure & Environments
52 | 5. Infrastructure & Environments | Set up Development environment | Developer | Not Started
53 | 5. Infrastructure & Environments | Set up QA environment | Developer | Not Started
54 | 5. Infrastructure & Environments | Set up Production environment | Developer | Not Started
55 | 5. Infrastructure & Environments | Configure separate environment variables, databases, storage and secrets per environment | Developer | Not Started
56 | 5. Infrastructure & Environments | Document Environment Configuration in the project folder | Developer | Not Started
57 | 5. Infrastructure & Environments | Define the Backup Policy: scope, frequency, retention period and storage location | Team Lead | Not Started
58 | 5. Infrastructure & Environments | Define and document RPO (Recovery Point Objective) and RTO (Recovery Time Objective) | Team Lead | Not Started
59 | 5. Infrastructure & Environments | Configure automated database backups for QA and Production (PostgreSQL / MongoDB / ClickHouse) | Developer | Not Started
60 | 5. Infrastructure & Environments | Configure backups for object storage, file storage and configuration/secrets | Developer | Not Started
61 | 5. Infrastructure & Environments | Enable encryption at rest and restrict access to all backup buckets | Developer | Not Started
62 | 5. Infrastructure & Environments | Store backups in a separate location/region from the primary environment | Developer | Not Started
63 | 5. Infrastructure & Environments | Configure backup failure alerting and monitoring | Developer | Not Started
64 | 5. Infrastructure & Environments | Perform a restore drill and verify data integrity of the restored copy | QA | Not Started
65 | 5. Infrastructure & Environments | Document the Backup & Restore Procedure in the Deployment folder | Team Lead | Not Started
66 | 5. Infrastructure & Environments | Verify masking rules before any Production backup is restored to a lower environment | Team Lead | Not Started
67 | 5. Infrastructure & Environments | Take a verified pre-deployment backup before each Production release | Developer | Not Started
68 | 5. Infrastructure & Environments | Set up the Build pipeline | Developer | Not Started
69 | 5. Infrastructure & Environments | Set up the Automated Testing pipeline | QA | Not Started
70 | 5. Infrastructure & Environments | Set up the Deployment pipeline (fully automated and repeatable) | Developer | Not Started
71 | 5. Infrastructure & Environments | Define and document the Rollback strategy | Team Lead | Not Started
72 | 5. Infrastructure & Environments | Set up branching per GitFlow: main, develop, feature, bugfix, hotfix, release | Team Lead | Not Started
73 | 5. Infrastructure & Environments | Enforce branch protection: no direct commits to main or develop | Team Lead | Not Started
6. Development
74 | 6. Development | Develop features per the approved design and coding standards | Developer | Not Started
75 | 6. Development | Follow frontend standards: React functional components, hooks, one component per file | Developer | Not Started
76 | 6. Development | Manage all server state via TanStack Query; Zustand only for shared state | Developer | Not Started
77 | 6. Development | Validate every API request and response using Zod | Developer | Not Started
78 | 6. Development | Use shadcn/ui as the standard component library; no new UI libraries without approval | Developer | Not Started
79 | 6. Development | Enforce ESLint, Prettier and TypeScript strict mode | Developer | Not Started
80 | 6. Development | Follow Go standards: gofmt, golangci-lint, structured logging, context propagation | Developer | Not Started
81 | 6. Development | Apply error wrapping, dependency injection and API versioning | Developer | Not Started
82 | 6. Development | Write Unit Tests for backend services | Developer | Not Started
83 | 6. Development | Follow database standards (PostgreSQL / MongoDB / ClickHouse) per guidelines | Developer | Not Started
84 | 6. Development | Raise Merge Requests for every change; delete branches after merge | Developer | Not Started
85 | 6. Development | Complete one Peer Review per Merge Request | Developer | Not Started
86 | 6. Development | Complete one Lead Review per Merge Request | Team Lead | Not Started
87 | 6. Development | Verify code quality, readability, performance, security, test coverage, architecture compliance | Team Lead | Not Started
88 | 6. Development | Create and maintain API Documentation | Developer | Not Started
89 | 6. Development | Update task status before Daily Scrum and move tasks to the correct Kanban status | Developer | Not Started
90 | 6. Development | Post End-of-Day update: work completed, progress, blockers, next-day plan | Developer | Not Started
7. Observability & Analytics
91 | 7. Observability & Analytics | Implement structured logging (ELK / Loki) | Developer | Not Started
92 | 7. Observability & Analytics | Implement correlation IDs and request tracing | Developer | Not Started
93 | 7. Observability & Analytics | Expose metrics and health endpoints; configure Prometheus | Developer | Not Started
94 | 7. Observability & Analytics | Build Grafana dashboards (application, infrastructure, database) | Developer | Not Started
95 | 7. Observability & Analytics | Configure API latency, error and resource utilisation monitoring | Developer | Not Started
96 | 7. Observability & Analytics | Configure alerting for critical failures | Developer | Not Started
97 | 7. Observability & Analytics | Prepare the Event Design Sheet before implementation | Product Team | Not Started
98 | 7. Observability & Analytics | Define event name, description, trigger, screen, attributes and business outcome | Product Team | Not Started
99 | 7. Observability & Analytics | Prepare the Analytics Tracking Plan and Event Dictionary | Product Team | Not Started
100 | 7. Observability & Analytics | Prepare User Journey Mapping | Product Team | Not Started
101 | 7. Observability & Analytics | Implement analytics (the platform the analytics ADR names) | Developer | Not Started
102 | 7. Observability & Analytics | Implement user, session and platform attributes on every event | Developer | Not Started
103 | 7. Observability & Analytics | Ensure unique user identification across sessions and devices | Developer | Not Started
104 | 7. Observability & Analytics | Verify analytics dashboards: funnel, adoption, retention, conversion, drop-off | QA | Not Started
8. Quality Assurance
105 | 8. Quality Assurance | Involve QA from requirement analysis onwards | QA | Not Started
106 | 8. Quality Assurance | Write Test Cases and map them to Acceptance Criteria | QA | In Progress | Meera Iyer | 2026-10-02 | Overdue badge cases pending the badge wording
107 | 8. Quality Assurance | Execute Functional Testing | QA | Not Started
108 | 8. Quality Assurance | Execute API Testing | QA | Not Started
109 | 8. Quality Assurance | Execute UI Testing | QA | Not Started
110 | 8. Quality Assurance | Execute Security Testing | QA | Not Started
111 | 8. Quality Assurance | Execute Performance Testing (where applicable) | QA | Not Started
112 | 8. Quality Assurance | Execute Cross Browser and Cross Device Testing (where applicable) | QA | Not Started
113 | 8. Quality Assurance | Build the UI Automation suite | QA | Not Started
114 | 8. Quality Assurance | Build the API Automation suite | QA | Not Started
115 | 8. Quality Assurance | Build the Regression Automation suite | QA | Not Started
116 | 8. Quality Assurance | Integrate automation into the CI/CD pipeline | QA | Not Started
117 | 8. Quality Assurance | Log every bug in the tracker, linked to its User Story | QA | Not Started
118 | 8. Quality Assurance | Include severity, priority, steps to reproduce, expected/actual result, screenshots | QA | Not Started
119 | 8. Quality Assurance | Retest fixes and close bugs | QA | Not Started
120 | 8. Quality Assurance | Support UAT in the QA environment (if applicable) | QA | Not Started
121 | 8. Quality Assurance | Provide QA sign-off before Production deployment | QA | Not Started
9. Security
122 | 9. Security | Run Dependency Scan | Developer | Not Started
123 | 9. Security | Run Secret Scan | Developer | Not Started
124 | 9. Security | Run Static Code Analysis | Developer | Not Started
125 | 9. Security | Conduct Security Review with Claude Code (vapt-report) | Team Lead | Not Started
126 | 9. Security | Conduct Vulnerability Assessment and generate the VAPT Report | Team Lead | Not Applicable | Kavya Rao |  | Northwind runs its own VAPT under the master agreement
127 | 9. Security | Fix all Critical and High vulnerabilities | Developer | Not Started
128 | 9. Security | Resolve Medium vulnerabilities wherever feasible before production | Developer | Not Started
129 | 9. Security | File the Security Review Document and VAPT Scan Report in the project folder | Team Lead | Not Started
10. Release & Deployment
130 | 10. Release & Deployment | Assign the release Version Number | Team Lead | Not Started
131 | 10. Release & Deployment | Prepare Release Notes | Team Lead | Not Started
132 | 10. Release & Deployment | Prepare the Deployment Checklist and Deployment Guide | Developer | Not Started
133 | 10. Release & Deployment | Prepare the Rollback Plan | Team Lead | Not Started
134 | 10. Release & Deployment | Prepare the User Guide and Known Issues & Limitations document | Product Team | Not Started
135 | 10. Release & Deployment | Confirm QA sign-off is obtained | QA | Not Started
136 | 10. Release & Deployment | Deploy to Production through the approved pipeline only | Developer | Not Started
137 | 10. Release & Deployment | Execute Smoke Testing post-deployment | QA | Not Started
138 | 10. Release & Deployment | Complete Production Verification | QA | Not Started
139 | 10. Release & Deployment | Confirm the full release checklist is complete before closing the release | Team Lead | Not Started
11. Artefacts & Documentation
140 | 11. Artefacts & Documentation | PRD, User Stories and Acceptance Criteria filed and current | Product Team | Completed |  |  | evidence: docs/product/backlog.md
141 | 11. Artefacts & Documentation | HLD, LLD, Architecture Diagram and Database Design filed and current | Team Lead | Completed |  |  | evidence: docs/design/orders-hld.md
142 | 11. Artefacts & Documentation | API Documentation and Environment Configuration filed and current | Developer | Not Started
143 | 11. Artefacts & Documentation | Test Cases and Automation Test Suite filed and current | QA | Completed |  |  | evidence: docs/testing/test-cases.md
144 | 11. Artefacts & Documentation | Event Design Sheet, Tracking Plan, User Journey Mapping, Event Dictionary filed | Product Team | Not Started
145 | 11. Artefacts & Documentation | Security Review Document and VAPT Report filed | Team Lead | Not Started
146 | 11. Artefacts & Documentation | Deployment Guide, Release Notes, User Guide, Known Issues filed | Team Lead | Not Started
147 | 11. Artefacts & Documentation | Backup Policy and Backup & Restore Procedure filed and current | Team Lead | Not Started
12. Communication & Governance
148 | 12. Communication & Governance | Document all major technical decisions | Team Lead | Not Started
149 | 12. Communication & Governance | Document and get approval for every requirement change | Product Team | Not Started
150 | 12. Communication & Governance | Communicate risks and blockers immediately | Developer | Not Started
151 | 12. Communication & Governance | Route all client communication through the Product Owner / Project Manager | Product Team | Not Started
152 | 12. Communication & Governance | Capture and circulate meeting notes | Team Lead | Not Started
153 | 12. Communication & Governance | Complete assigned learning paths and share knowledge with the team | Developer | Not Started
154 | 12. Communication & Governance | Conduct project retrospective and capture process improvements | Team Lead | Not Started